## May 2025 Active Projects
| Project Name | Project Mgr | Phase | Target Date | Status | Prog
1 | Athletics(ADF) aquatic therapy pool | NYoungblood | Closing | Summer 2025 | In-Progress | Yes
2 | Campus Damage Freeze 2022 - Insurance | SClaybon | Closing | Summer2025 | In-Progress | Yes
3 | Campus Damage Freeze 2024 - Insurance | SClaybon | Closing | Spring 2025 | Funding | Review
4 | Lambuth Varnell-Jones Water Damage- Insurance | SClaybon | Closing | Summer 2025 | Budgeting | Review
5 | Patterson Hall – 2023 Storm Damage - Insurance | SClaybon | Closing | Summer 2025 | In-Progress | Yes
6 | Alumni Building Mold evaluation/repairs | GKeen | Conceptual | Summer 2025 | TBD | Yes
7 | Art Building – Sawdust collection/Exhaust/Safety | GKeen | Conceptual | TBD | Review | Yes
8 | Art ADA Bathroom installation/ADA | GKeen | Conceptual | TBD | Consulting | N/A
9 | Billy Mac Jones HVAC evaluation 75%RH | GKeen | Conceptual | Spring 2025 | In-Progress | Yes
10 | Central Boiler Plant #5 Abatement and Demolition | TBD | Conceptual | TBD | Budgeting | Review
11 | CERI Security Fencing/Security | GKeen | Conceptual | Winter 2024 | Budgeting | Review
12 | Community Health Clinical Labs | GKeen | Conceptual | TBD | In-Progress | Yes
13 | Engineering Technology Research Generator | SClaybon | Conceptual | Consulting | In-Progress | Yes
14 | FCBE SBC Planning | PPoteet | Conceptual | TBD | In-Progress | Yes
15 | Innovation Garage improvements- safety (PG1) | GKeen | Conceptual | Winter 2025 | TBD | Yes
16 | Jones Hall Roof Strategy (Sealer) | GKeen | Conceptual | Summer2025 | In-Progress | Yes
17 | Lambuth Carney-Johnston Kitchenette | GKeen | Conceptual | TBD | TBD | N/A
18 | LLC HVAC Program | SClaybon | Conceptual | Fall 2025 | In-Progress | N/A
19 | LLC Domestic Water Pressure upgrade | SClaybon | Conceptual | Winter 2025 | In-Progress | N/A
20 | Millington/CAESAR Earth Science Storage | GKeen | Conceptual | Summer2025 | In-Progress | Yes
21 | Newport Rooftop HVAC | SClaybon | Conceptual | TBD | In-Progress | Yes
22 | Recreation Center/Natatorium pool temp management | SClaybon | Conceptual | TBD | Budgeting | Hold
| South Hall (Boiler,Mold,HVAC,Showers) eval - ResLife | SClaybon | Conceptual | Summer 2025 | In-Progress | N/A
23 | South Hall Domestic Boiler - ResLife | SClaybon | Conceptual | Summer 2026 | Budgeting | Review
24 | Wilder Tower 2nd fl Drinking Fountain | RWalker | Conceptual | TBD | Budgeting | Review
26 | Wilder Tower Air Filtration Systems | SClaybon | Conceptual | Summer 2026 | Consulting | Yes
27 | ACB Building – Physical Plant HVAC corrections | Lkane | Construction | Spring 2025 | Consulting | Review
28 | Admin Breezeway | NYoungblood | Construction | Summer 2025 | Consulting | Review
29 | Admin Government Relations Office | NYoungblood | Construction | Summer 2025 | Consulting | Review
30 | Art Building – Silica collection/Exhaust/Safety | NYoungblood | Construction | Summer2025 | Budgeting | Yes
31 | Athletics(P3) – Dormitory | LHicks | Construction | Fall 2026 | Budgeting | Yes
32 | Campus Site Bollards - Phase 1 Gate Protection | GKeen | Construction | Summer2025 | In-Progress | Review
33 | Campus Site Gates – Walker, Bookstore, Norriswood | PHolder | Construction | Summer 2025 | Ph-1 | Review
34 | Centennial Place Low pressure domestic water control | SClaybon | Construction | Winter2025 | In-Progress | Yes
35 | Central Boiler Plant Controls Integration for Hawk System | SClaybon | Construction | Fall 2025 | Consulting | Yes
36 | Central Chiller Plant Stabilize parapet keys | LHicks | Construction | Summer2025 | In-Progress | Yes
37 | Central chiller plant tower #1 installation | LHicks | Construction | Summer 2025 | In-Progress | Yes
38 | Central Chiller Plant Chiller Installation | LHicks | Construction | Summer 2025 | In-Progress | Yes
39 | Chemistry Fume Hood commissioning | LHicks | Construction | Summer2025 | In-Progress | Yes
40 | Chemistry Plant Control Upgrades to Trane UC600 | JWilson | Construction | Winter 2025 | TBD | Yes
41 | Chemistry Roof Replacement | LHicks | Construction | Summer 2026 | Funding | Review
42 | Clement Hall Fan Coil Repairs | NYoungblood | Construction | Summer 2025 | In-Progress | Yes
43 | Community Health Chiller Warranty Corrections | SClaybon | Construction | TBD | In-Progress | Yes
44 | Engineering Science compressed air system | SClaybon | Construction | Summer 2025 | Budgeting | Yes
45 | Engineering Technology Roof Top HVAC 50ton | LHicks | Construction | Summer2025 | Budgeting | Yes
46 | Engineering Technology Roof Replacement | LHicks | Construction | Summer 2025 | In-Progress | Yes
47 | Engineering Solar Smart-grid lab | SClaybon | Construction | Summer 2025 | Budgeting | Yes
48 | ERIC/Stem Building Machine Shop Power Distribution | PHolder | Construction | Summer 2025 | Budgeting | Yes
49 | International Center Study Abroad Offices | NYoungblood | Construction | Fall 2025 | In-Progress | Yes
50 | Johnson Hall Selected Paint and Patch | RWalker | Construction | Summer 2025 | In-Progress | Yes
51 | Johnson Hall Miracle Method Bathrooms 1st Floor | RWalker | Construction | Summer 2025 | In-Progress | Yes
52 | Johnson Hall HVAC - Auditorium Units HVAC | PHolder | Construction | Winter 2025 | In-Progress | Yes
53 | Johnson Hall HVAC - Basement HVAC Unit East | PHolder | Construction | Winter 2025 | Budgeting | Yes
54 | Johnson Hall Refinish Non-Classroom Doors | RWalker | Construction | Summer 2025 | TBD | TBD
55 | Johnson Hall Fan Coil Corrections | SClaybon | Construction | Summer2025 | TBD | TBD
56 | Jones Hall West Split System HVAC | SClaybon | Construction | Summer2025 | In-Progress | Yes
57 | Kemmons Wilson Holiday Inn Canopy Roof Replacement | LHicks | Construction | Summer2025 | Review | Review
58 | Kemmons Wilson Holiday inn - North Bollards | GKeen | Construction | Summer 2025 | Funding | Review
59 | Lambuth Hyde Hall DPT Program Improvements | GKeen | Construction | Summer 2025 | Funding | Yes
60 | Lambuth Hyde Hall Fire Alarm and Electrical Improvements | SClaybon | Construction | Summer 2025 | TBD | TBD
61 | Lambuth Hyde Hall Basement HVAC Improvements | SClaybon | Construction | Summer2025 | TBD | TBD
62 | Life Sciences Roof Replacement (SBC) | LHicks | Construction | Spring 2026 | Budgeting | Yes
63 | Life Science Greenhouse HVAC improvements | SClaybon | Construction | Summer 2025 | TBD | TBD
64 | McWherter Library Cooling Tower Motor | JBoyland | Construction | Summer 2025 | Funding | Review
65 | Mitchell Hall ADA Signage | NYoungblood | Construction | Summer 2025 | Funding | Review
66 | Mitchell Fan coil corrections | NYoungblood | Construction | Summer 2025 | Funding | Review
67 | Mitchell Roof Sealer - Baker Roofing | NYoungblood | Construction | Summer 2025 | In-Progress | Yes
68 | Mynders Hall Demolition | LHicks | Construction | Summer 2025 | In-Progress | Yes
69 | Patterson Hall Fan Coil Control Upgrade - Phase 1 | SClaybon | Construction | Summer 2025 | Budgeting | Yes
70 | Patterson Hall Fan Coil Control Upgrade - Phase 2 | SClaybon | Construction | Winteer 2025 | In-Progress | Yes
71 | Patterson Hall – Basement Stormwater flood control | NYoungblood | Construction | Summer2025 | In-Progress | Yes
72 | Police Hub - Police Services | RWalker | Construction | Summer 2025 | Hold | Hold
73 | Psychology Animal Facility - Monitor/Control | SClaybon | Construction | Winter 2025 | In-Progress | Yes
74 | Psychology 4th floor VAV controls/ Wireless to Wired | SClaybon | Construction | Fall 2025 | Budgeting | Review
75 | Rawls West Entry | NYoungblood | Construction | Summer 2025 | In-Progress | Yes
76 | Rose Theatre Steam Decommission | SClaybon | Construction | Winter 2025 | TBD | TBD
77 | Smith Hall Dorm East Entry - Main | NYoungblood | Construction | Summer 2025 | Budgeting | TBD
78 | Utility – South Campus Water Wells (MLGW) | SClaybon | Construction | Summer 2025 | Budgeting | N/A
79 | Zach Curlin/Police Services Central Dispatch/Security | RWalker | Construction | Summer 2025 | Budgeting | N/A
80 | Athletics(ADF) student success center | NYoungblood | Design | Fall 2026 | Budgeting | N/A
81 | Athletics Soccer Field Locker Facility | LHicks | Design | TBD | Budgeting | N/A
82 | Engineering Technology - 1st Floor Ladies Room (SBC) | PHolder | Design | Spring 2026 | Budgeting | Yes
83 | ERIC/Stem Laser Cutter Exhaust | SClaybon | Design | Summer 2025 | TBD | Hold
84 | McWherter Dining Services - Einstein Bagels Remodel | SClaybon | Design | Summer 2025 | TBD | TBD
85 | Fieldhouse Controls | SClaybon | Funding | Winter 2025 | Review | Yes
86 | Hayden Hall AFROTC Student Center Floor | NYoungblood | Funding | Summer 2025 | TBD | TBD
87 | Herzog File Room (Mold) - Ph 1 (Loose Documents) | RWalker | Funding | Summer2025 | TBD | TBD
88 | Herzog File Room (Mold) - Ph 1 (Filed Plan Documents) | RWalker | Funding | TBD | TBD | TBD
89 | Admin OIE office- access Aiphone/Security | RWalker | Planning | Fall 2025 | In-Progress | Yes
90 | Admin East 2nd floor Corridor Repairs | NYoungblood | Planning | Winter 2025 | Budgeting | Yes
91 | Admin Bldg Boiler/Hydronic Heating (SBC) | PHolder | Planning | TBD | Budgeting | Review
92 | Alumni Water Supply Deadleg Auto-Flush | SClaybon | Planning | TBD | Budgeting | TBD
93 | Ball Hall Stair Fire Stopping System | LHicks | Planning | Winter 2025 | Budgeting | Review
94 | Campus - Goodman Street Enhanced Lighting | SClaybon | Planning | TBD | In-Progress | Yes
95 | Campus April 2025 Insurance Claim | SClaybon | Planning | TBD | In-Progress | Yes
96 | Campus Parking Lot Paving/Repairs | NYoungblood | Planning | TBD | In-Progress | Yes
97 | Campus Lot 20 Striping | GKeen | Planning | TBD | TBD | TBD
98 | Campus Perimeter Door Access/Security | DJamison | Planning | TBD | Review | Yes
99 | Campus Master Plan/ Residence Life | PPoteet | Planning | TBD | In-Progress | Yes
100 | Campus Thumb-turn Mortise Lock/Security | GKeen | Planning | TBD | In-Progress | Yes
101 | Campus Lock-Down/Security | SClaybon | Planning | TBD | In-Progress | Yes
102 | Campus Sidewalk Repairs (2025) | NYoungblood | Planning | Fall 2025 | In-Progress | Yes
103 | Campus School Cross Walk/Safety | DJamison | Planning | Winter 2025 | TBD | TBD
104 | Cecil Humphreys Law School Korean Memorial Bollards | GKeen | Planning | TBD | In-Progress | Yes
105 | Central Boiler Plant Softener and Blow Down | SClaybon | Planning | Winter 2025 | In-Progress | Yes
106 | CERI Research Modernization | LHicks | Planning | TBD | Consulting | Review
107 | CERI EQ4 Data Center/ Leibert/ Humidity Control | SClaybon | Planning | Winter 2025 | Budgeting | Yes
108 | CERI EQ2 New Faculty Office | RWalker | Planning | Summer 2025 | TBD | TBD
109 | Chemistry 405 Structural Repairs | RWalker | Planning | Fall 2025 | Budgeting | Yes
110 | Chemistry 407 Structural Repairs | RWalker | Planning | Fall 2025 | Budgeting | Yes
111 | Chemistry Bathrooms 1st fl | GKeen | Planning | Winter 2025 | Budgeting | Review
112 | Chemistry teaching labs improvements - lighting | RWalker | Planning | Winter 2025 | In-Progress | Yes
113 | Chemistry teaching labs improvements - paint and patch | RWalker | Planning | Winter 2025 | In-Progress | Yes
114 | Chemistry Computer Lab Carpet to LVT | RWalker | Planning | Winter 2025 | In-Progress | Yes
115 | Chemistry Stair Treads | RWalker | Planning | Summer 2025 | TBD | TBD
116 | Chemistry Research Modernization | LHicks | Planning | TBD | Review | Hold
117 | Clement Research Modernization | LHicks | Planning | TBD | In-Progress | Yes
118 | Defense Audit -ALSAC HVAC- Lease | SClaybon | Planning | Fall 2025 | In-Progress | Yes
119 | Dunn Hall Research Modernization (SBC) | LHicks | Planning | TBD | In-Progress | Yes
120 | Ellington Hall Research Modernization (SBC) | LHicks | Planning | TBD | In-Progress | Yes
121 | Ellington Stair Treads (Repair only) | RWalker | Planning | Summer 2025 | Budgeting | Review
122 | Engineering Research Modernization | LHicks | Planning | TBD | In-Progress | Yes
123 | Engineering Science 113 Lab Remodel | SClaybon | Planning | Winter 2025 | TBD | TBD
124 | Engineering Science 323A improvements | SClaybon | Planning | Winter 2025 | TBD | TBD
125 | Engineering Science 325 improvements | SClaybon | Planning | Winter 2025 | In-Progress | Yes
126 | Engineering Technology - Polytechnic Offices | RWalker | Planning | Summer 2025 | In-Progress | Yes
127 | FedEx (FIT) Stormwater containment | SClaybon | Planning | TBD | Consulting | Review
128 | Fieldhouse Domestic Hot Water | SClaybon | Planning | TBD | Consulting | Review
129 | Fieldhouse Visitor Locker Shower Corrections | SClaybon | Planning | Winter 2025 | TBD | TBD
130 | Fieldhouse Gymnasium Security | TBD | Planning | TBD | TBD | TBD
131 | Fieldhouse Locker Room Security | TBD | Planning | TBD | In-Progress | Yes
132 | Fieldhouse Boiler Plant – Ph 2 | SClaybon | Planning | Winter 2025 | In-Progress | Review
133 | Fieldhouse Generator – Research Freezer (SBC) | SClaybon | Planning | TBD | In-Progress | Yes
134 | Fieldhouse Research Modernization (SBC) | LHicks | Planning | TBD | TBD | TBD
135 | Fogelman B&E Renovation (SBC) | PHolder | Planning | TBD | Budgeting | Review
136 | Fogelman Admin (SBC) | PHolder | Planning | TBD | TBD | TBD
137 | Hayden Hall Boiler/Hydronic Heating (SBC) | PHolder | Planning | TBD | Budgeting | Yes
138 | Highland Library Roof | GKeen | Planning | TBD | Consulting | Review
139 | International Building Central Windows | LHicks | Planning | Summer 2026 | In-Progress | Yes
140 | Johnson Hall Research Modernization (SBC) | LHicks | Planning | TBD | In-Progress | Yes
141 | Johnson Hall Boiler/Hydronic Heating (SBC) | PHolder | Planning | TBD | In-Progress | Yes
142 | Johnson Hall East Steps and Rails | LHicks | Planning | Summer 2026 | In-Progress | Yes
143 | Johnson Hall Main Entry Granite Panel Repair | LHicks | Planning | Winter 2025 | In-Progress | Yes
144 | Johnson Hall Basement corrections -Research Space | SClaybon | Planning | Winter 2025 | Consulting | Review
145 | Johnson Hall Basement – ADA improvements | SClaybon | Planning | Winter 2025 | In-Progress | Yes
146 | Jones Cafeteria - Boiler/Hydronic Heating (SBC) | PHolder | Planning | TBD | In-Progress | Yes
147 | Jones Cafeteria – Entry Portico Landing | GKeen | Planning | Summer2025 | In-Progress | Yes
148 | Jones Hall Stair Fire Stopping System | LHicks | Planning | Summer 2026 | In-Progress | Yes
149 | Kemmons Wilson Hospitality/Culinary Relocation | PPoteet | Planning | TBD | In-Progress | Yes
150 | Lambuth Varnell-Jones Testing Center Furniture and move | CDickinson | Planning | Summer2025 | In-Progress | Yes
151 | Lambuth Varnell-Jones Testing Center Alteration | GKeen | Planning | Winter 2025 | TBD | TBD
152 | Life Science Research Modernization (SBC) | LHicks | Planning | TBD | In-Progress | Yes
153 | Life Science Emerg Power Electron Microscope Lab (SBC) | SClaybon | Planning | TBD | In-Progress | Yes
154 | ManningHall Research Modernization (SBC) | LHicks | Planning | TBD | Budgeting | Review
155 | Manning Hall Boiler/Hydronic Heating (SBC) | PHolder | Planning | TBD | Consulting | Review
156 | McWherter Library Special Collections/Leibert/ Humidity | SClaybon | Planning | Fall 2026 | In-Progress | Yes
157 | McWherter Library Boiler/Hydronic Heating (SBC) | Pholder | Planning | TBD | Budgeting | Review
158 | McWherter Library Writing center door opener | RWalker | Planning | Summer2025 | TBD | TBD
159 | Meeman Journalism Boiler/Hydronic Heating | PHolder | Planning | TBD | In-Progress | Yes
160 | Meeman Journalism Bathrooms - | GKeen | Planning | Winter 2025 | Consulting | Review
161 | Mitchell HVAC Select Fresh Air and Noise reduction | NYoungblood | Planning | Summer 2025 | In-Progress | Yes
162 | Patterson Hall Steps - Spalling Concrete | NYoungblood | Planning | Summer 2025 | Consulting | Review
163 | Psychology Research Modernization | LHicks | Planning | TBD | Consulting | Review
164 | Rawls Hall Stair rails | NYoungblood | Planning | Summer 2025 | In-Progress | Yes
165 | Rawls Chilled Water System Hydronic Flush-ResLife | SClaybon | Planning | Summer 2025 | Consulting | N/A
166 | Rawls Domestic Hot Water Boiler - | SClaybon | Planning | Summer 2026 | Budgeting | Review
167 | Rawls LP Steam Boiler Plant Connection/Heating- ResLife (SBC) | SClaybon | Planning | TBD | TBD | TBD
168 | Recreation Center Boiler Room Roof Repairs | NYoungblood | Planning | Winter 2025 | TBD | TBD
169 | SFPAC Stage Canopy Modification | LHicks | Planning | Summer 2025 | In-Progress | Yes
170 | University Center Boiler/Hydronic Heating (SBC) | PHolder | Planning | TBD | Budgeting | Review
171 | Utility – Generators Recertification | JMoss | Planning | Fall 2025 | In-Progress | Yes
172 | Wellness Center -Cooking Hood/Lighting Controls | NYoungblood | Planning | Summer 2025 | In-Progress | Yes
173 | Wilder Tower stair exit discharge upgrades | LHicks | Planning | Summer 2026 | In-Progress | Yes
174 | Wilder Tower Mechanical 3rd Floor Sealing Leaks | PHolder | Planning | Winter 2025 | In-Progress | Yes
175 | Wilder Tower Bursar Office HVAC/Corrections | RWalker | Planning | Winter 2025 | Budgeting | Review
176 | Wilder Tower Bursar Entry Carpet/Flooring Replacement | RWalker | Planning | Winter 2025 | Budgeting | Review
177 | Wilder Tower E/W Main Entry Doors | SClaybon | Planning | Winter 2025 | Budgeting | Review
178 | Wilder Tower Transformer Maintenance/Replacement | JMoss | Planning | TBD | Budgeting | Review
179 | SFPAC Spotlight Room HVAC | SClaybon | Planning | Summer 2025 | In-Progress | Yes
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195

## 24-25 Completed Projects
| Project Name | Project Mgr | Phase | Target Date | Status
1 | Admin President’s office -access/Security | RWalker | Construction | Winter 2024 | Complete
2 | Admin Provost office – access/Security | RWalker | Construction | Winter 2024 | Complete
3 | Admin Bi-Directional Antenna/Security | RWalker | Conceptual | Spring 2025 | Complete
4 | Athletics(ADF) Football Coach Roof | NYoungblood | Construction | Fall 2025 | Complete
5 | Brister Hall Roof Replacement | LHicks | Construction | Spring 2025 | Complete
6 | Campus Lighting Improvements - South Campus | PHolder | Construction | Spring 2025 | Complete
7 | Campus Lot 20 Fencing/Security | SClaybon | Construction | Spring 2025 | Complete
8 | Campus School Ballistic Film/Security | NYoungblood | Construction | Spring 2025 | Complete
9 | Cecil Humphreys Law School - Hall of Judges | NYoungblood | Construction | Summer 2025 | Complete
10 | Cecil Humphreys Law School - Signage | NYoungblood | Construction | Summer 2025 | Complete
11 | Central Chiller Plant 2300V Transformer | JMoss | Construction | Spring 2025 | Complete
12 | CFA Deans Suite alteration | NYoungblood | Construction | Summer2025 | Cancel
13 | Chemistry 425 HVAC installation | LHicks | Construction | Winter 2024 | Complete
14 | Chemistry 403 Structural repairs | RWalker | Construction | Winter 2024 | Complete
15 | Chemistry Elevator cooling units | LHicks | Construction | Spring 2025 | Complete
16 | Clement Generator | SClaybon | Construction | Winter 2024 | Complete
17 | Ellington Hall Generator | SClaybon | Construction | Winter 2024 | Complete
18 | Engineering Science Fume Hood Commissioning | LHicks | Construction | Winter 2024 | Complete
19 | Engineering Technology transformer replacement | JMoss | Construction | Winter 2024 | Complete
20 | ERIC/Stem Welding Fume Containment | SClaybon | Construction | Spring 2025 | Complete
21 | ERIC/Stem Building Deans Lab | PHolder | Construction | Winter 2024 | Complete
22 | FedEx (FIT) Entry Repairs/-insurance | SClaybon | Construction | Spring 2025 | Complete
23 | Fieldhouse Boiler Plant- Ph 1 | SClaybon | Construction | Winter 2024 | Complete
24 | Health Center - Police Services Conference Room/Security | RWalker | Construction | Winter 2024 | Complete
25 | Herzog Boiler Plant | SClaybon | Construction | Winter 2024 | Complete
26 | Hudson Health Hydronic Heating system | SClaybon | Construction | Winter 2024 | Complete
27 | Hudson Health Air Quality/Well Certification | RWalker | Construction | Spring 2025 | Complete
28 | Hudson Health Emergency Lighting/Well Certification | RWalker | Construction | Spring 2025 | Complete
29 | Hudson Health Video Entry – Security | RWalker | Funding | Spring 2025 | Cancel
30 | International Center Recruitment Offices | NYoungblood | Construction | Spring 2025 | Complete
31 | Johnson Hall Bathroom Partitions and Lighting | PHolder | Construction | Winter 2024 | Complete
32 | Johnson Hall Lighting | PHolder | Construction | Winter 2024 | Complete
33 | Johnson Hall HVAC- Fresh Air Units | PHolder | Construction | Winter 2024 | Complete
34 | Kemmons Wilson Holiday Inn Main Roof Replacement | LHicks | Construction | Spring 2025 | Complete
35 | Kemmons Wilson Holiday Inn rolling gate | SClaybon | Construction | Spring 2025 | Complete
36 | Life Science basement (Animal center hvac) and Egress | LHicks | Construction | Spring 2025 | Complete
37 | Life Science Chiller Maintenance (SBC) | LHicks | Construction | Spring 2025 | Complete
38 | Lipman School Ballistic Film/Security | NYoungblood | Construction | Spring 2025 | Complete
39 | Lipman School Fire Alarm system/Safety | SClaybon | Construction | Winter 2024 | Complete
40 | McWherter Library Fire Alarm upgrade | LHicks | Construction | Winter 2024 | Complete
41 | Millington/ CAESAR Earth Science Lab -Conceptual only | GKeen | Conceptual | Summer2025 | Complete
42 | Mynders Hall TVA Energy Grant | SClaybon | Planning | Summer2026 | In-Progress
43 | Newport Damage - insurance | SClaybon | Construction | Spring 2024 | Complete
44 | Orgel School Ballistic Film/Security | NYoungblood | Construction | Spring 2025 | Complete
45 | Orgel High School Lab | LHicks | Construction | Winter 2024 | Complete
46 | Patterson Hall Mechanical Lighting | PHolder | Planning | Spring 2025 | Complete
47 | Patterson Hall – furniture replacement | CDickinson | Planning | Spring 2025 | Complete
48 | Psychology Animal Facility- emergency generator | SClaybon | Construction | Winter 2024 | Complete
49 | Rawlins Book Store Remodel- Student Aux. | SClaybon | Construction | Winter 2024 | Complete
50 | Rawls Lobby AHU | SClaybon | Conceptual | Spring 2025 | Complete
51 | Robison Hall Drinking Fountain | RWalker | Funding | TBD | Cancel
52 | Smith Hall Dorm Entry – ADA | NYoungblood | Construction | Winter 2024 | Complete
53 | University Center Bi-Directional Antenna | RWalker | Planning | TBD | Complete
54 | University Center Domestic Water Boiler | SClaybon | Construction | Winter 2024 | Complete
55 | University Center Amazon Go Market | SClaybon | Construction | Winter 2024 | Complete
56 | Wilder Tower Windows | PHolder | Construction | Winter 2024 | Complete
57 | Wilder Tower HVAC (3rd fl-South) | PHolder | Construction | Winter 2024 | Complete
58 | Wilder Tower HVAC controls | PHolder | Planning | Summer 2025 | Complete
59 | Wilder Tower High-pressure NGas Relief Improvements | SClaybon | Construction | Winter 2024 | Complete
60 | Wilder Tower Financial Aid Office Remodel | GKeen | Conceptual | Spring 2025 | Cancel
61 | Zach Curlin / Bi-Directional Antenna- Security | RWalker | Construction | Winter 2024 | Complete