## Project Name
Summer Compensation Phase II - 9 month faculty
|  |  | Start Date | Due Date | Resources | Complete Date | Comments
1 | Initiate Project
| 1.1 | Team Kick-off Meeting | 2011-11-01 | 2011-11-01 |  | Complete
| 1.2 | Define "Pains & Issues" | 2011-11-09 | 2011-11-09
| 1.3 | Review "TO BE" process | 2011-11-09 | 2011-11-09
2 | Electronic Signature
| 2.1 | Review UofM Electronic Signature Policy | 2011-11-04 |  | Dean
| 2.2 | Review TBR Guideline | 2011-11-04 |  | Dean
| 2.3 | Develop formal statement of process | 2011-11-04 |  | Dean
| 2.4 | CIO / VP ITD - review and approval | 2011-11-04 | 2011-11-15
3 | E-contract Updates
| 3.1 | remove printable contract option |  | 2011-11-01 | Christine | Complete
| 3.2 | send email notification to create EPAF |  | 2012-01-31 | Christine | Complete
| 3.3 | remove Grants Acct check box | ` | 2011-11-01 | Christine | Complete
| 3.4 | pay date - system generate? |  |  | Christine | Complete | issue last summer was the pay dates and the service dates Team decided not to add this feature
| 3.5 | add language for 90% rule |  | 2011-11-01 | Christine | Complete | cant get paid more than 90% of max compensation from sponsored program (Grant)
| 3.6 | revised fields are highlighted |  | 2011-11-01 | Christine | Complete
| 3.7 | EPAF friendly page in e-contract |  | 2011-11-01 | Christine | Complete
|  | Summer credit instruction dates |  |  | Christine |  | exist on GA Program guide page bf.memphis.edu want display under summer faculty page too
4 | EPAF Updates
| 4.1 | Change approval level 20 to approve |  | 2012-04-06 | Debbie
| 4.2 | Add field to enter contract number |  |  | Debbie | Complete
| 4.3 | Email notifications - turn on in Test |  |  | Debbie/Chris | Complete | just for team members
| 4.4 | Banner Security access |  |  | Debbie | Complete
| 4.5 | Make facsum EPAF not enterable for JCRE = sucom |  | 2011-11-08 | Debbie | Complete | Job code reason
5 | Action Items
| 5.1 | Add 'Best Practice' information to HR guide page |  | 2012-03-30 |  |  | Get team to provide some Best practice tips - example how to create Outlook folder and create filters
| 5.2 | Review email messages |  |  | 2012-01-31 | Complete | 11/16 team testing said the email message needs to be reviewed
| 5.3 | Create Revision/Termination "IF/THEN" doc |  |  | Team | Complete | Using GA document as a model, create document for 9 month Faculty sum comp
| 5.4 | Add Personnel Date field to EPAFS |  |  | Debbie
| 5.5 | Add contract field to EPAFs |  |  | Debbie | Complete
| 5.6 | EPAF - email notifications alert e-contract & EPAF differences |  | 2012-02-07 | Debbie/ITD | Complete | Debbie met with ITD and determine the specifications for the scripts
| 5.6a | Debbie will send Hyperion script to ITD |  | 2012-02-01 | Debbie | Complete | List of tables and fields that will be needed for ITD to use for triggers
| 5.6b | ITD write scripts that will initiate email notifications to originator and approver | 2012-02-02 | 2012-03-01 | Chris Renfrow | Complete | ITD will compare the e-Contract with the saved/submitted EPAF for any differences and email the originator and if submitted for approval to the approver Team began testing 2/14/2012
| 5.6c | Email notification when an EPAF is Void/Cancelled | 2012-02-02 | 2012-03-01 | Debbie/ Chris Renfrow | Complete | Debbie will contact ITD to work out the specifications
6 | Testing
| 6.1 | e-contract | 2011-11-16 | 2011-12-15 |  | Complete | Verify Service dates, Pay Dates, Salary
| 6.1 | e-contract testing - invite faculty | 2011-11-16 | 2011-11-16 |  | Complete | Faculty attended testing session on 11/16/2011
| 6.2 | EPAF's | 2012-01-16 | 2012-02-28 |  | Complete | Pre, Law, 1st Term, 1st Teacher, 2nd Term, 2nd Teacher, Full Summer, RODP, Summer Other/Extra Comp
| 6.3 | Test EPAF Termination | 2012-01-31 | 2012-02-28
| 6.4 | Test EPAF Revisions | 2012-01-31 | 2012-02-28 |  |  | Several Revision EPAFs were created and tested, Team decision is to have only one Revision EPAF
7 | Training Manual
| 7.1 | Update - add Revisions and Terminations/ IF THEN |  | 2012-03-01 |  |  | Team reviewed document 2/9/2012
|  | e-Contract - Summer Comp update document | 2012-01-30 | 2012-02-15 | DG,CM,OT, DF |  | David, Dean, Christine, Ora working on updates to the e-Contract documentation
|  | EPAF - Summer Comp update document | 2012-02-10 | 2012-02-28 | DW,VP,LJ,BW |  | Debbie, Vickie, Becky,Latisha will work on updates for EPAF document
|  | Create PowerPoint Presentation for Training |  | 2012-03-01 | Team
8 | Communication
| 8.1 | Emails to departments/chairs/deans |  | 2012-02-03 |  |  | process change is coming
| 8.2 | Emails to faculty |  | 2012-02-15
| 8.3 | Training - notification |  | 2012-02-20 | Dean/Ann Harbor | 2012-02-20 | Provost Chairs Support Staff; Provost Dean Support Staff; Provost College Business Officiers; Provost Dept Business Reps
|  | e-mail summer schedule reminder |  | 2012-03-01
9 | Campus Training
| 9.1 | Training for departments Training March 20,21,22,28,29 | 2012-03-20 | 2012-03-29 |  |  | David said we need to do more training this time to eliminate some of the problems from summer 2011. Schedule McWherter Library lab for training.Schedule for 1.5 hours each
|  | Have training scheduled in Learning Curve |  | 2012-03-15 | Dean | 2012-02-13
|  | Trainers for the sessions: |  | 3/20-22, 3/28-29 | Dean (20,22), Debbie (21), David G (28,29) | 2012-02-09
9 | Reports Review/Update
| 10.1 | Compare e-contract with banner and determine if approved contract does not have an applied EPAF |  | 2012-02-28 | Debbie/Patty
| 10.2 | Earn compensation by Term |  | 2012-03-30 | Dean/Nicole |  | Include F9, PF, GA. Goal is to replace the excel spreadsheets departments are creating for the Provost office
| 10.3 | Status of EPAF by College |  | 2012-03-30 | Debbie/Patty
10 | Go Live Readiness
| 9.1 | Turn on EPAF email notifications prod |  |  | Chris
| 9.2 | e-Contract - updates complete
| 9.3 | EPAF - Summer Comp EPAFs, Revisions, Termination- Final testing |  |  |  |  | Pre, Law, 1st Term, 1st Teacher, 2nd Term, 2nd Teacher, Full Summer, RODP, Summer Other/Extra Comp
| 9.13 | Reports tested and approved
| 9.14 | Banner HR Security
| 9.15 | EPAF approval security
| 9.16 | e-contract security
10 | Production Go-Live
| 10.1 | e-contract |  | 2012-04-06
| 10.2 | EPAFs - Revision & Termination created |  | 2012-04-06
11 | Policy Review
| 11.1 | UofM policy UM1493 does not reflect same verbiage as TBR 5:02:04:10. Add UoM verbiage for the 90% rule |  | 2012-03-15 | Dean
12 | End Project Wrk Session
| 12.1 | End of Project Working Session/Lunch |  |  |  |  | Holiday Inn
13 | Post Go-live Review
| 13.1 | Metric - measurable |  | 2012-07-10
| 13.2 | Meeting to review issues, success
14 | Postmortem | Schedule 8-12 weeks after go-live
|  | Lesson Learned | Team
Plan for long-term training needs
|  | Closeout with task force committee | Team
|  | Post Mortem Review | Team
PITF

## Issues
Project Plan Reference | Description | Issue Stated | Action Needed | Solution | Completed | Resource

## Project Team Resources
Core:
| Becky Ward | Engineering
| Christine MacDonald | BFSS | Business Finance System Support
| Colette Williams | ITD | Infromation Technology Division
| David Greganti | Engineering
| Dean Franklin | Provost
| Debbie Wooddell | BFSS | Business Finance System Support
| Latica Jones |  | Psychology
| Marjaret Ann Jarred | HRR | Human Resource Records
| Mary Mansour | CFA | College Fine Arts
| Ora Taylor-Strowder | ICL | Instruction Curriculum Leadership
| Vickie Peters |  | School Urban Affairs
| Yolanda Fleming | BFSS | Business Finance System Support
Resources:
Patty Murry
Chris Renfrow
Nicole McBride
Shelby Tate
Faculty Testing: