## Sheet1
2023-12-14
Agencies Involved | Overall Goal | Specific Tasks | Progress Status
UM; Hope House; Agape; Love Doesn't Hurt; ReportDV901 | Distribute 1,000 Ring Cameras to DV survivors in Shelby County | Establish protocol for ordering cameras | COMPLETE
|  | Create and Disseminate Flyers and social media content about cameras for distribution | In Progress
|  | Educational video training for agencies | In Progress
UM; YWCA; CAFTH, Claire’s House, NAREB | Seek funding from members of the Shelby County Board of Commissioners as wells as other potential funding sources. | Identify Flexible Funding for Shelter/Housing Repair | In Progress
| Seek funding for emergency shelter | CAFTH – hotel dollars for emergency shelter – there will be specific parts of this funding set aside for DV survivors | In Progress
1. Including the danger assessment as intake into database for coordinated entry
| Replace funding since the ending of COVID funding | Identify funding for shelter staff | In Progress
FSC; DA's Office; MPD; UM | Improve interdepartmental communication centered around ongoing domestic violence rapid response team (DVRRT) | Restructure DVRRT to connect high-risk survivors to services and build a the best possible case against perpetrator | COMPLETE
|  | Preparation protocol for DVRRT meetings | COMPLETE
|  | Consistently hold ongoing DVRRT meetings (twice a month) | In Progress
|  | Attend high risk meeting in Nashville | Not Started
|  | Refer Victims to DV clinic (MALS) | Not Started
|  | Identify metrics to understand success of the group | Not Started
|  | Complete review of high risk survivors caseload at each DVRRT meeting | In Progress
|  | Hire DVRRT Coordinator | Not Started
CVRCC; Heal901, Moms Demand Action. Crimestoppers, ReportDV901 | Target at-risk populations with domestic violence awareness education initiative | Identify middle and high schools in high DV areas | COMPLETE
|  | Increase funding for existing outreach programs | Not Started
|  | Increase access to schools and number of students reached | Not Started
|  | Finalize slide presentation for nurses and nursing students on DV response | Not Started
|  | Complete Nursing/Health Professional training | Not Started
|  | Complete training in Shelby County Youth Justice and Education Center | Not Started
UM, MPD, FSC, DA's Office, Bartlett PD | Streamline the process to distribute LAP to entities centered around bail decisions through implementation of electronic lethality assessment protocol (2.0) | Map current flow of LAP | COMPLETE
|  | FSC becomes a network member of Maryland Network Against Domestic Violence | In Progress
|  | LAP 2.0 piloted in one precinct | Not Started
|  | Develop and complete training with: officers, judges, magistrates, and 24 clerks | Not Started
|  | Confirm agencies using LAP 2.0 (roll out to whole county) | Not Started
FSC; YWCA; Love Doesn't Hurt; DA's Office; CAFTH CVRCC; UM; Bartlett PD | Explore viability of 24/7 response within domestic violence services | Share FSC data/develop understanding of need | In Progress
|  | Work to expand the YWCA shelter capacity in number of bed and expanded property | Not Started
|  | assess the capacity of domestic violence social service agencies to house 24/7 advocates for DV victims | Not Started
|  | Align the FSC structure to family justice center best practices. | In Progress