## Slide 1
EVENT PLANNING:
comprehensive guide

## Slide 2: PRE-PLANNING

## Slide 3: Step One: Start with an Idea

## Slide 4: The Idea:
Fill out the Basics:
  WHAT
    What is your event?
  WHEN
    When is your ideal date?
  WHY
    Why are you having this event? What is the purpose?
  WHO
    Who is the target audience?
  HOW
    How will this event be accomplished? How much time do you need?

## Slide 5: Step Two: Check dates

## Slide 6: Dates
On Campus:
  Utilize VEMS to check and solidify dates
  RSO’s can register space one year in advance in VEMS
Off Campus:
  Call venues to check dates and prices
  Prices for venues may vary depending on the time of year

## Slide 7: Step Three: Start a Budget

## Slide 8: Budget
Contact vendors to get quotes for your event this should include:
  Artist/speaking fees
  Facility fees
  Catering funds
  Giveaways
  Publicity Fees
  Food and refreshments
Assess the budget with your organization, if feasible begin planning the event

## Slide 9
PLANNING TIMELINE

## Slide 10: 12 WEEKS OUT
Contact artist/agency, gather information, check dates and finalize prices
Identify and invite community partners
Finalize the overall mission of the event.
Understand technical needs
  If the event is on campus, work with Conference and Event Services to confirm technical needs
Fill out the Event Registration form in TigerZone

## Slide 11: 11 WEEKS OUT
Begin working on publicity and brainstorming a marketing plan
  WHO is this event for? How are you going to target this event?
  Start creating graphics and understanding the overall feel of the event

## Slide 12: 10 WEEKS OUT
Finalized the publicity plan
Finalize space reservation process
  Ensure all proper forms are filled out with Conference and Event Services, Physical Plant, etc.
  If you need a STAGE you must work with Physical Plant to set it up.

## Slide 13: 9 WEEKS OUT
If a ticketed event, begin working on a ticket distribution plan
  If your event is in the Rose Theatre or University Center, explore the option of using memphis.edu/tigertix

## Slide 14: 8 WEEKS OUT
Place your carting order
  If on campus: Utilize Tiger Dining/Aramark.
    You can get quotes directly from their website
    If you do not see something you would like from Tiger Dining, contact them for custom dishes or options
Check on vendor contracts and begin finalizing
Create a supplies list and begin acquiring
Confirm community partners

## Slide 15: 6 WEEKS OUT
Begin publicizing your event
  Posters
    University Center – Take to UC 255 and email to ucmedia@memphis.edu
    Other Campus Buildings – Check with the office the bulletin boards are in front of
  Social Media
Follow up with vendors, if contracts and performance agreements are not signed
Arrange with police if your event is going to have more than 300 people (this will be noted in your Event Registration Form)

## Slide 16: 4 WEEKS OUT
Create a volunteer list for the day of your event
  Who do you need where?
    Greeters
    Hospitality
    Money Management
    Vendor Contacts
    Check In Table / Information Table
    This is event specific
Continue publicizing your event
Optional: Order t-shirts for your event
Review your event with Conference and Event Services.

## Slide 17: 3 WEEKS OUT
Update any necessary documents regarding day of timeline, contracts, catering, etc.
Check in with community partners
Continue event promotion
Start to finalize RSVPs
Follow up with vendors

## Slide 18: 2 WEEKS OUT
Finalize your supplies (started in week 8)
Finalize your volunteers and member roles for the day of the event
Send information to SGA E-News on TigerZone
  This will send your event out in an all school
  Be sure to include your graphic, any important links, and all pertinent event information

## Slide 19: 1 WEEK OUT
Social Media blasts
Finalize itinerary
Final contact with vendors
Confirm all arrangements
Walk through event with your organization, ideally in the physical space
Identify an Event Risk Manager

## Slide 20: DAY OF EVENT
Event planner and risk manager should be at the event the entire time
Work with vendors to get all elements in place
Continue publicizing on social media
Have FUN!
Utilize an in-event evaluation

## Slide 21: AFTER EVENT
Clean up
Remove all promotional material from campus
Evaluate the event with your organization
  Stars & Wishes
Thank You notes
Ensure payments have been complete
Create a Historical file for the next year

## Slide 22
CAMPUS PARTNERS

## Slide 23: CAMPUS PARTNERS
UNIVERSITY CENTER
  Lauren Shelley
    Manager Conference & Event Scheduling FIT & UC
    lauren.shelley@memphis.edu
ROSE THEATRE
  Lizzie Fudge
    Manager, Event Support & Services UC and Rose Theatre
    e.fudge@memphis.edu
POLICE
  Derek Myers
    Assistant Chief of Police, Director of Police Operations
    dmyers@memphis.edu
PARKING
  Tommy Miller
    Assistant Director, Parking & Transportation
    tmller19@memphis.edu
TIGER COPY & GRAPHICS
  tigercopygraphics@memphis.edu